Sixty-first session

Agenda item 144 (a)

Financing of the United Nations peacekeeping forces in the

Middle East: United Nations Disengagement Observer Force

Performance report on the budget of the United Nations 
Disengagement Observer Force for the period from 
1 July 2005 to 30 June 2006

Report of the Secretary-General

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| Introduction | 3 |
| Mandate performance | 3 |
| Resource performance | 8 |
| Financial resources | 8 |
| Monthly expenditure patterns | 9 |
| Other income and adjustments | 9 |
| Expenditure for contingent-owned equipment: major equipment and self-sustainment | 10 |
| Analysis of variances | 11 |
| Actions to be taken by the General Assembly | 12 |

Summary

The present report contains the performance report on the budget of the United Nations Disengagement Observer Force (UNDOF) for the period from 1 July 2005 to 30 June 2006.

The total expenditure for UNDOF for the period from 1 July 2005 to 30 June 2006 has been linked to the mission’s objective through a number of results-based frameworks, grouped by components, namely, operations and support.

Performance of financial resources (Thousands of United States dollars. Budget year is from 1 July 2005 to 30 June 2006.) Variance Category Apportionment Expenditure Amount Percentage Military and police personnel 20 137.7 20 223.8 (86.1) (0.4) Civilian personnel 8 377.0 7 867.5 509.5 6.1 Operational costs 13 006.7 12 025.6 981.1 7.5 Gross requirements 41 521.4 40 116.9 1 404.5 3.4 Staff assessment income 1 142.4 1 126.2 16.2 1.4 Net requirements 40 379.0 38 990.7 1 388.3 3.4 Voluntary contributions in kind (budgeted) — — — — Total requirements 41 521.4 40 116.9 1 404.5 3.4 . Human resources incumbency performance Category Approveda Actual (average) Vacancy rate (percentage)b Military contingents 1 047 1 043 0.4 International staff Posts 42 37 11.9 General temporary assistance — — — National staff Posts 107 104 3.2 General temporary assistance — — — a Represents the highest level of authorized strength. b Based on monthly incumbency.

The actions to be taken by the General Assembly are set out in section V of the present report.

I.	Introduction

1.	The budget for the maintenance of the United Nations Disengagement Observer Force (UNDOF) for the period from 1 July 2005 to 30 June 2006 was set out in the report of the Secretary-General of 21 December 2004 (A/59/653 and Corr.1 and 2) and amounted to $41,581,200 gross ($40,438,800 net). It provided for 1,047 military contingents, 42 international staff, 107 national staff. The Advisory Committee on Administrative and Budgetary Questions, in paragraph 31 of its report on UNDOF (A/59/736/Add.4), recommended that the General Assembly appropriate $41,581,200 gross for the period from 1 July 2005 to 30 June 2006.

2.	The General Assembly, by its resolution 59/306 of 22 June 2005, appropriated an amount of $41,521,400 gross ($40,379,000 net) for the maintenance of the mission for the period from 1 July 2005 to 30 June 2006. The total amount has been assessed on Member States.

II.	Mandate performance

3.	The mandate of the Force was established by the Security Council in its resolution 350 (1974) of 31 May 1974. The mandate for the performance period was provided by the Council in its resolutions 1605 (2005) of 17 June 2005 and 1648 (2005) of 21 December 2005.

4.	The Force is mandated to help the Security Council achieve an overall objective, namely, to maintain international peace and security.

5.	Within this overall objective, the Force has, during the performance report period, contributed to a number of accomplishments by delivering related key outputs, shown in the frameworks below. These frameworks are grouped by components: operations and support.

6.	The present report assesses actual performance against the planned results-based frameworks set out in the 2005/06 budget. In particular, the performance report compares the actual indicators of achievement, that is, the extent to which actual progress has been made during the period against the expected accomplishments, with the planned indicators of achievement, and compares the actually completed outputs with the planned outputs.

Component 1: operations

| Expected accomplishment 1.1: The parties act in accordance and comply with the Disengagement Agreement |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| 1.1.1 Separation of forces and areas of limitation maintained | Achieved: zero serious violations of the ceasefire agreement and 168 minor protested violations in the UNDOF area of responsibility |
| Planned outputs | Completed (number or yes/no) | Remarks |
| Weekly high-level meetings with the Syrian authorities; meetings with local Syrian officials, as needed | 23 | Meetings Fewer meetings than anticipated due either to Force Commander’s absence on official business or to scheduling conflicts |
| Monthly high-level meetings with the Israel Defence Force command | 9 | Same as above |
| Biweekly meetings with the Israel Defence Force liaison staff | 16 | Same as above |
| 21,900 mobile patrol person days (3 troops per patrol x 20 patrols x 365 days) | 29 711 | The increase in mobile patrols resulted from additional requirements in the area of separation to follow up on initial observation reports. Mobile patrols were also increased to compensate for suspension of some planned foot patrols owing to bad weather conditions |
| 8,030 foot patrol person days (2 troops x 11 patrols x 365 days) | 6 192 | Decrease in the number of actual foot patrols was the result of quick response by mobile patrols, as well as suspension of some foot patrols because of bad weather conditions |
| 7,300 standing patrol person days (2 troops x 10 patrols x 365 days) | 1 961 | The decrease in the actual number of standing patrol was a result of the modernization programme, which reduced the number of fixed positions |
| 5,840 night patrol person days (4 troops x 4 patrols x 365 days) | 5 846 |  |
| 10,950 rapid reaction patrol responses (2 troops x 15 responses x 365 days) within 10 minutes of call | 9 595 | Decrease in the actual number of rapid reaction responses was due to the increase in the number of actual mobile patrols |
| 13,875 troop manned observation post person days (2 troops x 19 positions x 365 days) | 15 158 | The number of fixed positions was increased from 19 to 20, resulting in a corresponding increase in troop-manned observation post person days |
| 1,460 temporary checkpoint person days (4 troops x 1 checkpoint x 365 days) | 2 041 | Increase in the actual number of temporary checkpoints was required as a result of additional new roads leading into the area of separation |
| Biweekly inspections of the areas of limitation | 26 | Completed inspections on both sides of the area of limitation |
| 2 reports of the Secretary-General to the Security Council | 2 | Reports |
| Immediate communications with the parties during crisis situations | Yes | Close contact maintained between UNDOF and both parties on a 24/7 basis |
| Periodic secure escort for International Committee of the Red Cross passage of persons across the area of separation for humanitarian purposes | Yes | UNDOF assisted in 2 crossings of students, 1 handover of a mentally handicapped boy, 1 crossing for a wedding, 1 family crossing (for medical treatment) and the crossing of 270 pilgrims |

| Expected accomplishment 1.2: Reduced threat of mines in the area of separation |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| 1.2.1 Zero persons killed/injured by mines and unexploded ordnance | • Zero persons killed, one person injured by mines and unexploded ordnance |
| Planned outputs | Completed (number or yes/no) | Remarks |
| Clearance of mines and unexploded ordnance in the area of separation | 258 | Mines and unexploded ordnance in the area of separation were cleared |
| Advice to the United Nations Children’s Fund (UNICEF) mine awareness project | No | No requests received |

Component 2: support

| Expected accomplishment 2.1: Effective and efficient logistical, administrative and security support to the mission |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| 2.1.1 Reduction in average procurement informal solicitations processing time between the receipt of certified requisitions and the issuance of purchase orders from 90 days in 2004/05 to 81 days in 2005/06 | • Achieved, average processing time: 80 days |
| 2.1.2 Reduction in time taken to submit contingent strength and contingent-owned equipment verification reports to Headquarters from an average of 25 days in 2003/04 to 15 days in 2004/05 to 10 days in 2005/06 | • Achieved. 10 days taken for inspection, verification and report submission |
| Planned outputs | Completed (number or yes/no) | Remarks |
| Service improvements |  |  |
| Streamlining of procurement paper flow by development of templates and maximized e-mail usage | Yes |  |
| Streamlining of processing of contingent-owned equipment and troop strength verification reports | Yes |  |
| Military personnel |  |  |
| Emplacement, rotation and repatriation for an average troop strength of 1,047 | Yes | Rotations completed |
| Supply and storage of rations to 2 camps and 19 positions for an average troop strength of 1,047 | Yes | Rations provided Positions were increased from 19 to 20 during the period |
| Civilian personnel |  |  |
| Administration of an average number of 42 international and 107 national staff | Yes | 37 international and 104 national staff contracts administered |
| Facilities and infrastructure |  |  |
| Maintenance of facilities in Camp Faouar, Camp Ziouani, Representational Office in Damascus, military police detachment “C” in the area of separation, 19 area of separation positions and 18 outposts | Yes | Completed Positions were increased from 19 to 20 while outposts were decreased from 18 to 8 during the period |
| Operation and maintenance of 95 generators in 24 locations | Yes | Completed |
| Repair of 8 kms of roads | Yes | Completed |
| Maintenance of 14 water wells and filtration systems | Yes | Completed |
| Ground transportation |  |  |
| Operation and maintenance of 372 vehicles, including 14 armoured personnel carriers | Yes | Completed |
| Support and maintenance of 12 PABX, 1,154 telephone extensions, 2 satellite Earth stations, 462 two-way mobile radios, 291 handy talkies, 18 VHF repeaters stations and 15 microwave sites | Yes | Completed |
| Information technology |  |  |
| Support and maintenance of a wide-area network, 38 servers, 401 desktop computers, 42 laptops, 181 printers and 28 scanners in 22 locations | Yes | Continuous data support services provided to the Force; over 96 per cent system uptime |
| Medical |  |  |
| Operation and maintenance of 3 level-1 medical centres for mission and United Nations Truce Supervision Organization (UNTSO) personnel and local civilian population in emergency cases | 5 728 | Patients treated |
| Operation and maintenance of HIV voluntary confidential counselling and testing facilities for all personnel | Yes |  |
| HIV sensitization programme for all personnel, including peer education | 883 |  |
| Security |  |  |
| Provision of security, including security threat assessment and risk management, to Camp Faouar, Camp Ziouani, Representational Office in Damascus, military police detachment “C” in the area of separation and 19 area of separation positions | Yes | Positions were increased from 19 to 20 during the period |
| Investigation of security incidents and advice to mission personnel and their dependants as well as to the personnel of 9 United Nations agencies | 194 | Cases investigated |
| Conduct of training exercises, encompassing procedures relating to security, nuclear, chemical and biological protection, shelter alarms and camp protection | 1 188 | Participants |

III.	Resource performance

A.	Financial resources

(Thousands of United States dollars. Budget year is from 1 July 2005 to 30 June 2006.)

| Category | Apportionment | Expenditures |  | Variance |
| --- | --- | --- | --- | --- |
|  |  |  | Amount | Percentage |
|  | (1) | (2) | (3)=(1)–(2) | (4)=(3)÷(1) |
| Military and police personnel |  |  |  |  |
| Military observers | — | — | — | — |
| Military contingents | 20 137.7 | 20 223.8 | (86.1) | (0.4) |
| Civilian police | — | — | — | — |
| Formed police units | — | — | — | — |
| Subtotal | 20 137.7 | 20 223.8 | (86.1) | (0.4) |
| Civilian personnel |  |  |  |  |
| International staff | 6 169.1 | 5 696.7 | 472.4 | 7.7 |
| National staff | 2 207.9 | 2 170.8 | 37.1 | 1.7 |
| United Nations Volunteers | — | — | — | — |
| Subtotal | 8 377.0 | 7 867.5 | 509.5 | 6.1 |
| Operational costs |  |  |  |  |
| General temporary assistance | 40.0 | 361.8 | (321.8) | (804.5) |
| Government-provided personnel | — | — | — | — |
| Civilian electoral observers | — | — | — | — |
| Consultants | — | 75.4 | (75.4) | — |
| Official travel | 229.6 | 282.2 | (52.6) | (22.9) |
| Facilities and infrastructure | 5 684.2 | 5 599.5 | 84.7 | 1.5 |
| Ground transportation | 3 380.5 | 2 440.2 | 940.3 | 27.8 |
| Air transportation | — | — | — | — |
| Naval transportation | — | — | — | — |
| Communications | 1 593.6 | 1 378.3 | 215.3 | 13.5 |
| Information technology | 781.1 | 714.4 | 66.7 | 8.5 |
| Medical | 346.8 | 392.7 | (45.9) | (13.2) |
| Special equipment | 203.6 | 158.2 | 45.4 | 22.3 |
| Other supplies, services and equipment | 747.3 | 622.9 | 124.4 | 16.6 |
| Quick-impact projects | — | — | — | — |
| Subtotal | 13 006.7 | 12 025.6 | 981.1 | 7.5 |
| Gross requirements | 41 521.4 | 40 116.9 | 1 404.5 | 3.4 |
| Staff assessment income | 1 142.4 | 1 126.2 | 16.2 | 1.4 |
| Net requirements | 40 379.0 | 38 990.7 | 1 388.3 | 3.4 |
| Voluntary contributions in kind (budgeted) | — | — | — | — |
| Total requirements | 41 521.4 | 40 116.9 | 1 404.5 | 3.4 |

B.	Monthly expenditure pattern

Monthly expenditures

7.	Higher expenditures in September 2005 were attributable to the recording, in the UNDOF special account, of obligations for the reimbursement of troop-contributing Governments for troop costs, major equipment and self-sustainment as well as for the provision of rations for military contingents.

C.	Other income and adjustments

(Thousands of United States dollars)

| Category | Amount |
| --- | --- |
| Interest income | 944.2 |
| Other/miscellaneous income | 381.1 |
| Voluntary contributions in cash | — |
| Prior-period adjustments | — |
| Savings on or cancellation of prior-period obligations | 2 870.7 |
| Total | 4 196.0 |

D.	Expenditure for contingent-owned equipment: major equipment and self-sustainment

(Thousands of United States dollars)

| Category | Expenditure |
| --- | --- |
| Major equipment |  |
| Military observers | — |
| Military contingents | 289.2 |
| Formed police units | — |
| Subtotal | 289.2 |
| Self-sustainment |  |
| Facilities and infrastructure |  |
| Catering (kitchen facilities) | 137.1 |
| Office equipment | 23.9 |
| Electrical | — |
| Minor engineering | 81.1 |
| Laundry and cleaning | — |
| Tentage | — |
| Accommodation | — |
| Miscellaneous general stores | 120.0 |
| Unique equipment | — |
| Field defence stores | — |
| Communications | — |
| Medical |  |
| Medical services | 82.7 |
| Special equipment |  |
| Explosive ordnance disposal | 45.4 |
| Observation | 0.4 |
| Identification | — |
| Nuclear, biological and chemical protection | — |
| Subtotal | 490.6 |
| Total | 779.8 |

| Mission factors | Percentage | Effective date | Last review date |
| --- | --- | --- | --- |
| A. Applicable to mission area |  |  |  |
| Extreme environmental condition factor | — | 19 May 2003 | 19 January 2006 |
| Intensified operational condition factor | — | 19 May 2003 | 19 January 2006 |
| Hostile action/forced abandonment factor | — | 19 May 2003 | 19 January 2006 |
| B. Applicable to home country |  |  |  |
| Incremental transportation factor | 0.0-2.75 |  |  |

IV.	Analysis of variances

|  | Variance |
| --- | --- |
| International staff | $472.4 | 7.7% |

8.	The unutilized balance was due primarily to lower actual costs than budgeted for common staff costs and an actual vacancy rate of 11.9 per cent compared to 7 per cent budgeted. The amount budgeted for common staff costs was based on 81 per cent of net salaries while the actual rate was 69.1 per cent.

|  | Variance |
| --- | --- |
| General temporary assistance | ($321.8) | (804.5%) |

9.	The additional requirements under this heading were due primarily to the need to recruit two staff to work on the UNDOF mapping project.

|  | Variance |
| --- | --- |
| Consultants | ($75.4) |  |

10.	The expenditures incurred against this line item represent the service fees for a consultant to serve as legal adviser to the Force Commander. A post has since been established in the mission for this purpose.

|  | Variance |
| --- | --- |
| Official travel | ($52.6) | (22.9%) |

11.	The additional requirements were due to several trips undertaken in connection with the replacement of the Canadian contingent and participation by mission staff in a number of training courses organized by the Department of Peacekeeping Operations for which initial budgetary provision had not been made.

|  | Variance |
| --- | --- |
| Ground transportation | $940.3 | 27.8% |

12.	The unspent balance under this heading was primarily due to non-procurement of 10 vehicles owing to the fact that eight 4x4 vehicles were received from the United Nations Interim Force in Lebanon (UNIFIL) and the fact that the planned acquisition of two armoured ambulances was postponed pending verification as to whether two M-113 vehicles could be upgraded and appropriately equipped for that purpose.

|  | Variance |
| --- | --- |
| Communications | $215.3 | 13.5% |

13.	The unutilized balance resulted primarily from delayed implementation of the expansion of carrier capacity on the satellite transponder and non-procurement of some equipment because interested vendors could not be identified.

|  | Variance |
| --- | --- |
| Information technology | $66.7 | 8.5% |

14.	The unspent balance was due primarily to the fact that the actual cost of equipment purchased was lower than budgeted.

|  | Variance |
| --- | --- |
| Medical | ($45.9) | (13.2%) |

15.	The additional requirements under this heading resulted primarily from expenditures incurred for the mission’s prorated share of the cost of stockpiling supplies for the treatment of avian flu.

|  | Variance |
| --- | --- |
| Special equipment | $45.4 | 22.3% |

16.	The unutilized balance resulted from lower-than-budgeted actual costs for night compass range finder/binoculars.

|  | Variance |
| --- | --- |
| Other supplies, services and equipment | $124.4 | 16.6% |

17.	The unspent balance was due primarily to the fact that fewer maps were purchased than initially planned. Instead, the mission recruited two staff under general temporary assistance to produce much of its requirements.

V.	Actions to be taken by the General Assembly

18.	The actions to be taken by the General Assembly in connection with the financing of UNDOF are:

(a)	To decide that Member States shall waive their respective shares in other income for the period ended 30 June 2006 amounting to $4,196,000 and their respective shares in the amount of $84,400 from the unencumbered balance of $1,404,500 for the period ended 30 June 2006, to be applied to meeting the current and future after-service health insurance liabilities of the United Nations;

(b)	To decide on the treatment of the remaining unencumbered balance of $1,320,100 for the period ended 30 June 2006.

# Footnotes

Resource variance amounts are expressed in thousands of United States dollars. Analysis is provided for variances of at least plus or minus 5 per cent and $100,000.

# Text boxes

—

2,000

4,000

6,000

8,000

10,000

12,000

14,000

16,000

Thousands of United States dollars         .

July

2005

August

2005

September

2005

October

2005

November

2005

December

2005

January

2006

February

2006

March

2006

April

2006

May

2006

June

2006