Sixty-first session

Agenda item 144 (b)

Financing of the United Nations peacekeeping forces in the
Middle East: United Nations Interim Force in Lebanon

Performance report on the budget of the United Nations Interim Force in Lebanon for the period from 1 July 2005 to 30 June 2006

*	The delay in the submission of the present report was due to the need for additional substantive consultations.

Report of the Secretary-General*

Contents

|  |  |  | Page |
| --- | --- | --- | --- |
| Introduction | 3 |
| Mandate performance | 3 |
| Resource performance | 8 |
| Financial resources | 8 |
| Monthly expenditure patterns | 9 |
| Other income and adjustments | 9 |
| Expenditure for contingent-owned equipment: major equipment and self-sustainment | 10 |
| Value of non-budgeted contributions | 11 |
| Analysis of variances | 11 |
| Actions to be taken by the General Assembly | 13 |

Summary

The present report contains the performance report on the budget of the United Nations Interim Force in Lebanon (UNIFIL) for the period from 1 July 2005 to 30 June 2006.

The total expenditure for UNIFIL for the period from 1 July 2005 to 30 June 2006 has been linked to the Force’s objective through a number of results-based frameworks, grouped by the following components: operations and support.

Performance of financial resources (Thousands of United States dollars. Budget year is from 1 July 2005 to 30 June 2006.) Category Apportionment Expenditure Variance Amount Percentage Military and police personnel 39 143.1 40 777.8 (1 634.7) (4.2) Civilian personnel 33 937.7 30 340.8 3 596.9 10.6 Operational costs 21 172.1 20 145.6 1 026.5 4.8 Gross requirements 94 252.9 91 264.2 2 988.7 3.2 Staff assessment income 4 715.7 4 078.5 637.2 13.5 Net requirements 89 537.2 87 185.7 2 351.5 2.6 Voluntary contributions in kind (budgeted) — — — — Total requirements 94 252.9 91 264.2 2 988.7 3.2 Human resources incumbency performance Category Approveda Actual (average) Vacancy rate (percentage) Military contingents 2 000 1 997 0.2 International staff 125 100 19.7 National staff 339 294 13.3 a Represents the highest level of authorized strength. The actions to be taken by the General Assembly are set out in section V of the present report.

I.	Introduction

1.	The budget for the maintenance of the United Nations Interim Force in Lebanon (UNIFIL) for the period from 1 July 2005 to 30 June 2006 was set out in the report of the Secretary-General of 21 December 2004 (A/59/654) and amounted to $94,277,700 gross ($89,562,000 net). It provided for 2,000 military contingent personnel, 125 international staff and 339 national staff. The Advisory Committee on Administrative and Budgetary Questions recommended acceptance by the General Assembly of the Secretary-General’s proposal for the maintenance of UNIFIL for the period from 1 July 2005 to 30 June 2006 (see A/59/736/Add.3, para. 30).

2.	The General Assembly, by its resolution 59/307, appropriated the amount of $94,252,900 gross ($89,537,200 net) for the maintenance of the Force for the period from 1 July 2005 to 30 June 2006. The total amount has been assessed on Member States.

II.	Mandate performance

3.	The mandate of the Force was established by the Security Council in its resolutions 425 (1978) and 426 (1978). The mandate for the performance period was provided by the Council in its resolutions 1583 (2005), 1614 (2005) and 1655 (2006).

4.	The Force is mandated to help the Security Council achieve an overall objective, namely, to restore international peace and security.

5.	Within this overall objective, the Force has, during the performance report period, contributed to a number of accomplishments by delivering related key outputs, shown in the frameworks below. These frameworks are grouped by the following components: operations and support.

6.	The present report assesses actual performance against the planned results-based frameworks set out in the 2005/06 budget. In particular, the performance report compares the actual indicators of achievement, that is, the extent to which actual progress has been made during the period against the expected accomplishments, with the planned indicators of achievement and compares the actually completed outputs with the planned outputs.

Component 1: operations

| Expected accomplishment 1.1: the parties fully respect the Blue Line |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| Absence of air, sea or ground incursions or firing incidents across the Line | 196 air violations, 35 sea violations, 769 ground violations, 117 firing incidents recorded by UNIFIL |
| Planned outputs | Completed (number or yes/no) | Remarks |
| 178,850 mobile patrol person days (5 troops x 98 patrols x 365 days) | 186,150 | On average, 5 troops x 102 patrols x 365 days; the higher number was due to: (a) heightened tension along the Blue Line during the period from November 2005 to June 2006; and (b) more mobile patrols undertaken owing to the lower number of operational observation posts (46 compared with 51 planned) |
| 186,150 troop manned observation post person days (5 troops per post x 2 shifts x 51 observation posts x 365 days) | 167,900 | On average, 5 troops per post x 2 shifts x 46 observation posts x 365 days; the lower number was due to the fact that only 46 observation posts were operational compared with 51 planned because of operational factors and the need to increase the number of mobile patrols and to enforce the Force’s protection measures |
| 480 air patrol hours along the Blue Line | 472 |  |
| 180 investigation and operational movement flight hours | 180 |  |
| 2 reports of the Secretary-General to the Security Council | 2 |  |

| Expected accomplishment 1.2: normalization of the Government of Lebanon’s authority in southern Lebanon |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| Increased presence of Lebanese authorities in southern Lebanon compared to 2004/05 | 3,740 static and semi-permanent checkpoints manned by the Lebanese Army and the Joint Security Forces compared with 4,299 in 2004/05 and 3,887 patrols conducted by the Joint Security Forces compared with 6,639 in 2004/05 |
| Planned outputs | Completed (number or yes/no) | Remarks |
| Weekly liaison meetings and monthly high-level meetings with the parties on normalization of the situation in southern Lebanon | 120 | Liaison meetings with representatives of the Lebanese Army and of the Israel Defense Forces |
|  | 23 | High-level meetings with senior Lebanese and Israeli officials |
| Mediation on potential sources of conflict with the parties to defuse tension as and when it occurs | Yes | Mediation efforts related to 12 incidents |
| Continuous cooperation with Lebanese authorities, the United Nations Development Programme (UNDP), the United Nations Educational, Scientific and Cultural Organization, the United Nations Children’s Fund, the Food and Agriculture Organization of the United Nations, the Office of the United Nations High Commissioner for Refugees, the United Nations Volunteers, the Economic and Social Commission for Western Asia, the United Nations Mine Action Service and non-governmental organizations on humanitarian assistance to the local population. Areas of cooperation include needs assessment, provision of expertise and manpower and distribution of items provided by donors | 104 52 | Coordination meetings (twice per week on average) with donors, non-governmental organizations and with United Nations agencies on needs assessment, provision of expertise and manpower to distribute items provided by donors Weekly meetings with civilian authorities |
| Continuous collaboration on landmine clearance, including provision of maps and transfer of information on mine clearance with the Lebanese authorities and agencies | 52 | Weekly meetings with the National Demining Office, an accredited commercial mine clearance company, the Mines Advisory Group and UNDP, including the sharing of information (maps and photographs) with relevant agencies and with the International Management System for Mine Action |

Component 2: support

| Expected accomplishment 2.1: effective and efficient logistical, administrative and security support to the mission |
| --- |
| Planned indicators of achievement | Actual indicators of achievement |
| Increase in bandwidth for local area network from 100 MB (100 per cent of the network in 2004/05) to 1 GB (33 per cent of the network in 2005/06) | Achieved. 37 per cent of the network was increased to 1 GB |
| Reduction in vehicle accidents from 213 in 2003/04 to 192 in 2004/05 and to 173 in 2005/06 | Achieved. 165 vehicle accidents |
| Planned outputs | Completed (number or yes/no) | Remarks |
| Service improvement |  |  |
| Implementation of the first year of a 3-year network equipment modernization programme | Yes | 33 per cent of old network switches replaced to improve network bandwidth from 100 to 1,000 megabits per second |
| Implementation of a driver training programme for contingents | 450 | Contingent personnel trained |
| Military personnel |  |  |
| Emplacement, rotation and repatriation for an average troop strength of 2,000 | 1,997 | Contingent personnel on average |
| Supply and storage of rations at 42 military positions for an average troop strength of 2,000 | 42 | Military positions |
| Civilian personnel |  |  |
| Administration of an average number of 125 international and 339 national staff | 100 294 | International staff on average National staff on average; the lower numbers were due to the delayed recruitment of international and national staff. The classification exercise for 36 new national staff posts (functions previously performed under special service agreements) was carried out in late 2005 and the recruitment process began in early 2006 |
| Facilities and infrastructure |  |  |
| Maintenance and repair of 42 military positions, including 977 prefabricated and 161 solid accommodation and office buildings | 42 949 160 | Military positions Prefabricated accommodation Solid accommodation |
| Maintenance of 50 km of access roads to various military positions | 50 | Kilometres |
| Repair and maintenance of 16 helipads | 16 | Helipads |
| Ground transportation |  |  |
| Operation and maintenance of 722 vehicles, including 50 armoured vehicles, in 5 locations | 706 | Vehicles, including 46 trailers and 50 armoured vehicles; the lower number is due to the write-off and downsizing of the Force’s fleet |
| Air transportation |  |  |
| Operation and maintenance of 4 rotary-wing aircraft | 4 | Rotary-wing aircraft |
| Communications |  |  |
| Support and maintenance of 10 private automatic branch exchanges (PABX), 1,500 telephone extensions, 2 satellite Earth stations, 600 two-way mobile radios, 300 handy talkies, 40 VHF repeater stations and 55 microwave sites | 10 1,400 3 600 300 40 55 | PABX Telephone extensions Satellite Earth stations Two-way mobile radios Handy talkies VHF repeater stations Microwave sites |
| Information technology |  |  |
| Support and maintenance of wide-area network, 580 desktops, 45 servers, 82 laptops, 320 printers and 60 scanners in 10 locations | 699 58 119 379 60 | Desktops Servers Laptops Printers Scanners The higher numbers of desktops, servers, laptops and printers include items that had been written off but were awaiting disposal |
| Medical |  |  |
| Operation and maintenance of 5 level-I and 2 basic level medical centres for all mission personnel and for the local civilian population in emergency cases | 5 2 | Level-I Basic level |
| Operation and maintenance of HIV voluntary confidential counselling and testing facilities for all personnel | Yes |  |
| HIV sensitization programme for all personnel, including peer education | Yes | Including the distribution to both military and civilian personnel of 2,000 HIV/AIDS awareness materials in 6 languages (Russian, Hindi, English, Spanish, Arabic and French) and inclusion of HIV/AIDS sensitization in the induction training programme for UNIFIL personnel |
| Security |  |  |
| Provision of 24-hour security to 42 military positions, Force headquarters and UNIFIL House | Yes |  |
| Conduct of 4 information sessions on security awareness and contingency plans for 2,000 military personnel, 125 international and 339 national staff | 4 | Information sessions for international and national staff, as well as military personnel |

III.	Resource performance

A.		Financial resources

(Thousands of United States dollars. Budget year is from 1 July 2005 to 30 June 2006.)

| Category | Apportionment | Expenditure |  | Variance |
| --- | --- | --- | --- | --- |
|  |  |  | Amount | Percentage |
|  | (1) | (2) | (3)=(1)-(2) | (4)=(3)((1) |
| Military and police personnel |  |  |  |  |
| Military observers | — | — | — | — |
| Military contingents | 39 143.1 | 40 777.8 | (1 634.7) | (4.2) |
| Civilian police | — | — | — | — |
| Formed police units | — | — | — | — |
| Subtotal | 39 143.1 | 40 777.8 | (1 634.7) | (4.2) |
| Civilian personnel |  |  |  |  |
| International staff | 18 143.0 | 16 244.1 | 1 898.9 | 10.5 |
| National staff | 15 794.7 | 14 096.7 | 1 698.0 | 10.8 |
| United Nations Volunteers | — | — | — | — |
| Subtotal | 33 937.7 | 30 340.8 | 3 596.9 | 10.6 |
| Operational costs |  |  |  |  |
| General temporary assistance | 48.0 | 20.6 | 27.4 | 57.1 |
| Government-provided personnel | — | — | — | — |
| Civilian electoral observers | — | — | — | — |
| Consultants | — | — | — | — |
| Official travel | 335.1 | 370.4 | (35.3) | (10.5) |
| Facilities and infrastructure | 9 178.7 | 8 811.3 | 367.4 | 4.0 |
| Ground transportation | 4 445.6 | 3 584.4 | 861.2 | 19.4 |
| Air transportation | 1 648.7 | 1 757.6 | (108.9) | (6.6) |
| Naval transportation | — | — | — | — |
| Communications | 1 326.8 | 1 344.6 | (17.8) | (1.3) |
| Information technology | 1 195.3 | 1 168.2 | 27.1 | 2.3 |
| Medical | 763.0 | 1 109.7 | (346.7) | (45.4) |
| Special equipment | 531.2 | 531.7 | (0.5) | (0.1) |
| Other supplies, services and equipment | 1 699.7 | 1 447.1 | 252.6 | 14.9 |
| Quick-impact projects | — | — | — | — |
| Subtotal | 21 172.1 | 20 145.6 | 1 026.5 | 4.8 |
| Gross requirements | 94 252.9 | 91 264.2 | 2 988.7 | 3.2 |
| Staff assessment income | 4 715.7 | 4 078.5 | 637.2 | 13.5 |
| Net requirements | 89 537.2 | 87 185.7 | 2 351.5 | 2.6 |
| Voluntary contributions in kind (budgeted) | — | — | — | — |
| Total requirements | 94 252.9 | 91 264.2 | 2 988.7 | 3.2 |

B.	Monthly expenditure pattern

7.	Higher expenditures in September 2005 were attributable mainly to the reimbursement of troop-contributing countries for troop costs, contingent-owned equipment and the self-sustainment of military contingents.

C.	Other income and adjustments

(Thousands of United States dollars)

| Category | Amount |
| --- | --- |
| Interest income | 2 240.9 |
| Other/miscellaneous income | 807.3 |
| Voluntary contributions in cash | — |
| Prior-period adjustments | — |
| Savings on or cancellation of prior-period obligations | 11 990.2 |
| Total | 15 038.4 |

D.	Expenditure for contingent-owned equipment: major equipment and self-sustainment

(Thousands of United States dollars)

| Category | Expenditure |
| --- | --- |
| Major equipment |  |
| Military observers | — |
| Military contingents | 2 036.4 |
| Formed police units | — |
| Subtotal | 2 036.4 |
| Self-sustainment |  |
| Facilities and infrastructure |  |
| Catering (kitchen facilities) | 65.0 |
| Office equipment | 56.0 |
| Electrical | 68.7 |
| Minor engineering | 39.4 |
| Laundry and cleaning | 390.1 |
| Tentage | — |
| Accommodation | — |
| Miscellaneous general stores | 106.5 |
| Unique equipment | — |
| Field defence stores | — |
| Communications | 28.0 |
| Medical |  |
| Medical services | 313.6 |
| Special equipment |  |
| Explosive ordnance disposal | 110.7 |
| Observation | 398.6 |
| Identification | — |
| Nuclear, biological and chemical protection | — |
| Subtotal | 1 576.6 |
| Total | 3 613.0 |
| Mission factors | Percentage | Effective date | Last review date |
| A. Applicable to mission area |  |  |  |
| Extreme environmental condition factor | 0.60 | 11 August 2006 | 17 October 2006 |
| Intensified operational condition factor | 0.80 | 11 August 2006 | 17 October 2006 |
| Hostile action/forced abandonment factor | 2.3 | 11 August 2006 | 17 October 2006 |
| B. Applicable to home country |  |  |  |
| Incremental transportation factor | 0.25-2.00 |  |  |

E.	Value of non-budgeted contributions

(Thousands of United States dollars)

| Category | Actual value |
| --- | --- |
| Status-of-forces agreement | 1 304.3 |
| Voluntary contributions in kind (non-budgeted) | — |
| Total | 1 304.3 |

IV.	Analysis of variances

|  | Variance |
| --- | --- |
| Military contingents | ($1 634.7) | (4.2%) |

8.	The additional requirements are attributable primarily to the unforeseen and unbudgeted replacement of one engineering unit. The additional requirements were partly offset by the lower average rotation cost of $581 per person compared with the budgeted cost of $773 per person.

|  | Variance |
| --- | --- |
| International Staff | $1 898.9 | 10.5% |

9.	The unspent balance resulted from the higher vacancy rate of 20 per cent as compared with the budgeted vacancy factor of 6 per cent.

|  | Variance |
| --- | --- |
| National staff | $1 698.0 | 10.8% |

10.	The unspent balance resulted from the higher vacancy rate of 13 per cent as compared with the budgeted vacancy factor of 3 per cent. The higher vacancy rate was attributable to the delay in the completion of the classification of the 36 new posts, which was completed in late 2005.

|  | Variance |
| --- | --- |
| General temporary assistance | $27.4 | 57.1% |

11.	The unspent balance resulted from lower actual requirements for the replacement of staff on sick and maternity leave.

|  | Variance |
| --- | --- |
| Official travel | ($35.3) | (10.5%) |

12.	The additional requirements were attributable mainly to the unforeseen and unbudgeted travel of a predeployment team to a troop-contributing country in connection with the replacement of one engineering unit. In addition, the increased requirements resulted from the longer than planned duration of some training trips outside the mission area.

|  | Variance |
| --- | --- |
| Facilities and infrastructure | $367.4 | 4.0% |

13.	The unspent balance was attributable mainly to the lower level of acquisition of generators owing to the unavailability of the type of generator specified under the Headquarters systems contract. The unutilized balance also resulted from reduced requirements for construction, alteration and renovation services. The unutilized balance was partly offset by additional requirements for maintenance services as a result of the delayed conversion of 36 individual contractors on special service agreements to national posts approved as at 1 July 2005.

|  | Variance |
| --- | --- |
| Ground transportation | $861.2 | 19.4% |

14.	The unspent balance resulted from: (a) the cancellation of the planned acquisition of vehicles, pending the completion of the write-off of damaged/obsolete vehicles; (b) favourable contractual costs for the maintenance and repair of the Force’s armoured vehicle fleet; (c) reduced requirements for spare parts owing to improved management controls and lower requirements for armoured vehicles; and (d) lower premium costs under the worldwide vehicle liability insurance policy.

|  | Variance |
| --- | --- |
| Air transportation | ($108.9) | (6.6%) |

15.	The additional requirements were attributable mainly to the increase in the rental cost of helicopters from $1,583 to $1,852 per flight hour. The additional requirements were partly offset by the Force’s lower prorated share of the worldwide liability insurance coverage for rotary and fixed-wing aircraft.

|  | Variance |
| --- | --- |
| Medical | ($346.7) | (45.4%) |

16.	The additional requirements resulted mainly from the procurement of medical supplies related to the preparation for the avian flu threat.

|  | Variance |
| --- | --- |
| Other supplies, services and equipment | $252.6 | 14.9% |

17.	The unspent balance was attributable mainly to reduced requirements for training fees, supplies and services resulting from the rationalization of the Force’s training programme, including the conduct of training at Force headquarters whenever it was feasible and more cost-effective. The unutilized balance also resulted from reduced requirements for freight and related costs due to lower rates for customs clearance charges, the lower than planned volume of shipments and the consolidation of separate shipments into bulk shipments.

V.	Actions to be taken by the General Assembly

18.	The actions to be taken by the General Assembly in connection with the financing of UNIFIL are:

(a)	To decide that Member States shall waive their respective shares in other income for the period ended 30 June 2006 amounting to $15,038,400 and their respective shares in the amount of $273,800 from the unencumbered balance of $2,988,700 for the period ended 30 June 2006, to be applied to meeting the current and future after-service health insurance liabilities of the United Nations;

(b)	To decide on the treatment of the remaining unencumbered balance of $2,714,900 for the period ended 30 June 2006.

# Footnotes

Resource variance amounts are expressed in thousands of United States dollars. Analysis is provided for variances of at least plus or minus 5 per cent and $100,000.